## Risks - Qualititave
Qualitative risk register |  |  |  | Risk probability | [5 empty] | Risk impact
Delivery objective | Description |  |  | Probability | Score |  |  |  |  | Probability | Score
DO1 | Real time bus information system |  |  | Almost certain | 5 |  |  |  |  | Catastrophic | 5
DO2 | Priority signal upgrades |  |  | Likely | 4 |  |  |  |  | Major | 4
DO3 | Pre-emptive traffic management |  |  | Possible | 3 |  |  |  |  | Moderate | 3
DO4 | Integrated control system |  |  | Unlikely | 2 |  |  |  |  | Minor | 2
|  |  |  | Rare | 1 |  |  |  |  | Insignificant | 1
|  |  |  | Initial risk level | [5 empty] | Residual risk level |  |  |  |  | Cost impact
Risk identifier | Risk descriptions | Description of potential impact | Risk owner | Liklihood | Impact | L | I | Risk Rating | Mitigation actions | Liklihood | Impact | L | I | Risk Rating | Probablilty | Minimum | Most likely | Maximum | Expected value | P50 | P50 Sub totals
[15 empty] | % | £ | £ | £ | £ | £ | £
DO1 | Real time bus information
DO1R1 | Lack of co-ordination between authorities | System compatibility compromised resulting in unreliable RTI system | Derbyshire County Council | Possible | Major | 3 | 4 | 12 | Conduct stakeholder consultation to ensure consistency with existing systems | Unlikely | Moderate | 2 | 3 | 6 | 30% | 1000 | 0 | 3000 | 200 | 600
DO1R2 | Most beneficial sites not identified | Maximum benefit from RTI not realised | Derbyshire County Council | Possible | Minor | 3 | 2 | 6 | Feasibility completed and key site locations already identified by respective local authorities in consultation with local bus operators. | Rare | Minor | 1 | 2 | 2 | 10% | 0 | 0 | 0 | 0 | 0
DO1R3 | Back office system does not have capacity for processing required | Unreliable or non-functioning system resulting in loss of confidence in system and damaged reputation | Contractor | Unlikely | Major | 2 | 4 | 8 | Calculated system specification to ensure proposed capacity and allowance for future expansion | Rare | Moderate | 1 | 3 | 3 | 15% | 0 | 0 | 10000 | 250 | 750
DO1R4 | No availability of local power supplies | RTI signs cannot function | Contractor | Unlikely | Moderate | 2 | 3 | 6 | Use local power supply from lighting or alternative renewable supply such as solar | Rare | Minor | 1 | 2 | 2 | 10% | 0 | 20000 | 60000 | 2333.3333 | 3000
DO1R5 | Bus operators cease trading | Loss of investment in bus-mounted hardware | Derbyshire County Council | Unlikely | Moderate | 2 | 3 | 6 | RTI signs at bus stops will still function and can be integrated with any replacement service providers | Unlikely | Minor | 2 | 2 | 4 | 20% | 0 | 0 | 0 | 0 | 0
DO1R6 | Bus operators don't engage | Unwillingness of smaller bus operators to engage with the installation of RTI systems | Derbyshire County Council | Possible | Major | 3 | 4 | 12 | Conduct stakeholder consultation to explain scheme and convey potential benefits | Unlikely | Moderate | 2 | 3 | 6 | 30% | -50000 | -10000 | 0 | -4500 | -7500
DO1R7 | Vandalism of signs | RTI signs are destroyed or damaged | Derbyshire County Council | Likely | Minor | 4 | 2 | 8 | Specify vandal resistant signs and tamper-proof wiring | Unlikely | Minor | 2 | 2 | 4 | 20% | 5000 | 20000 | 100000 | 6166.6667 | 10500
[15 empty] | 0% | [5 empty] | 7350
DO2 | Priority signal upgrades | [13 empty] | 0%
DO2R1 | Most beneficial sites not identified | Maximum benefit from RTI not realised | Contractor | Possible | Moderate | 3 | 3 | 9 | Complete feasibility study and consult with bus operators | Rare | Minor | 1 | 2 | 2 | 10% | 0 | 0 | 0 | 0 | 0
DO2R2 | Bus routes change in future | Maximum benefit from RTI not realised | Derbyshire County Council | Possible | Minor | 3 | 2 | 6 | Locations to focus on key, long-established routes | Rare | Insignificant | 1 | 1 | 1 | 5% | 10000 | 20000 | 50000 | 1166.6667 | 1500
DO2R3 | Traffic signals not compatible | Reduced benefit from time savings at signal sites | Contractor | Unlikely | Moderate | 2 | 3 | 6 | Install at alternative sites instead | Unlikely | Insignificant | 2 | 1 | 2 | 10% | 2000 | 10000 | 20000 | 1033.3333 | 1100
[15 empty] | 0% | [5 empty] | 2600
DO3 | Premptive traffic management | [13 empty] | 0%
DO3R1 | Task start date is delayed | Compressed timescales for development, installation and difficulty completing project by end of FY2019. | DfT | Likely | Moderate | 4 | 3 | 12 | Use Midland Highway Alliance for contractor appointment. Process paperwork as early as possible and programme necessary activities as close to start data as possible. | Unlikely | Minor | 2 | 2 | 4 | 20% | 0 | 10000 | 20000 | 2000 | 2000
DO3R2 | Floating vehicle data not sufficiently rich or of sufficient quality | Inability to detect congestion build-up | Derbyshire County Council | Possible | Moderate | 3 | 3 | 9 | Initial discussions have taken place with a potential leading supplier of floating vehicle data. The suppliers’ system is mature and they have significant market penetration for the in-vehicle devices from which they collect data. | Unlikely | Minor | 2 | 2 | 4 | 20% | 0 | 20000 | 80000 | 5333.3333 | 8000
DO3R3 | Limited number of message signs may restrict benefit | Low user penetration for information distribution | Derbyshire County Council | Possible | Moderate | 3 | 3 | 9 | Use of mobile VMS will enable flexibility for sign locations | Rare | Minor | 1 | 2 | 2 | 10% | 0 | 0 | 0 | 0 | 0
DO3R4 | Equipment costs more expensive than initial research suggests | Funding obtained will not allow full potential to be reached | Contracted supplier | Possible | Moderate | 3 | 3 | 9 | Flexibility in scheme will allow a reduction in scope to accommodate hanges | Unlikely | Minor | 2 | 2 | 4 | 20% | 10000 | 50000 | 100000 | 10333.3333 | 11000
DO3R5 | Data costs for expansion are more than anticipated | Potential cost increases to achieve same benefit as anticipated | Contracted supplier | Possible | Moderate | 3 | 3 | 9 | Seek early consultation with prospective data providers to ensure competitive costs and quality is provided | Unlikely | Moderate | 2 | 3 | 6 | 30% | 0 | 20000 | 80000 | 8000 | 12000
DO3R6 | Mobile VMS signs vandalised or stolen | No benefit to drivers from sign location and cost required for replacement | Derbyshire County Council | Possible | Minor | 3 | 2 | 6 | Use GPS enabled mobile VMS signs to track signs if they are stolen. | Unlikely | Minor | 2 | 2 | 4 | 20% | 5000 | 50000 | 100000 | 10166.6667 | 10500
[15 empty] | 0% | [5 empty] | 43500
DO4 | Integrated control system | [13 empty] | 0%
DO4R1 | Lack of integration with surrounding counties | Inconsistent RTI or unreliable, resulting in less benefit | Contracted supplier | Possible | Major | 3 | 4 | 12 | Consult local authorities to ensure consistency and compatibility | Rare | Minor | 1 | 2 | 2 | 10% | 10000 | 20000 | 50000 | 2333.3333 | 3000
DO4R2 | No spare office location to house control system | Real time benefit minimised due to lack of monitoring | Derbyshire County Council | Possible | Moderate | 3 | 3 | 9 | Identify spare office space in advance, or use remote cloud hosted services | Unlikely | Insignificant | 2 | 1 | 2 | 10% | 1000 | 5000 | 10000 | 516.6667 | 550
DO4R3 | Lack of understanding of control system | No staff knowledge results in system not being used | Derbyshire County Council | Possible | Major | 3 | 4 | 12 | Ensure operational training manuals are provided and training is delivered | Rare | Minor | 1 | 2 | 2 | 10% | 0 | 3000 | 10000 | 366.6667 | 500
DO4R4 | Integration of proprietary services could be restricted by limitations in APIs to the proprietary services | Limited scope of intended functionality | Contracted supplier | Possible | Moderate | 3 | 3 | 9 | Early investigation of interfaces to different system components and consultation with potential suppliers to establish agile system development and delivery | Rare | Minor | 1 | 2 | 2 | 10% | 5000 | 20000 | 30000 | 1916.6667 | 1750
[8 empty] | 1 | [5 empty] | 1
[8 empty] | 2 | [5 empty] | 2
[8 empty] | 3 | [5 empty] | 3
[8 empty] | 4 | [5 empty] | 4
[8 empty] | 5 | [5 empty] | 5
[8 empty] | 6 | [5 empty] | 6
[8 empty] | 7 | [5 empty] | 7
[8 empty] | 8 | [5 empty] | 8
[8 empty] | 9 | [5 empty] | 9
[8 empty] | 10 | [5 empty] | 10
[8 empty] | 11 | [5 empty] | 11
[8 empty] | 12 | [5 empty] | 12
[8 empty] | 13 | [5 empty] | 13
[8 empty] | 14 | [5 empty] | 14
[8 empty] | 15 | [5 empty] | 15
[8 empty] | 16 | [5 empty] | 16
[8 empty] | 17 | [5 empty] | 17
[8 empty] | 18 | [5 empty] | 18
[8 empty] | 19 | [5 empty] | 19
[8 empty] | 20 | [5 empty] | 20
[8 empty] | 21 | [5 empty] | 21
[8 empty] | 22 | [5 empty] | 22
[8 empty] | 23 | [5 empty] | 23
[8 empty] | 24 | [5 empty] | 24
[8 empty] | 25 | [5 empty] | 25
5800
[15 empty] | Total | -1000 | 258000 | 723000 | 47616.6667 | 59250

## Risks - Quantified
|  |  | Severity | [7 empty] | Severity
|  |  | 5 | 4 | 3 | 2 | 1 |  |  |  | 5 | 4 | 3 | 2 | 1
|  |  | catastrophic | major | moderate | minor | insignificant |  |  |  | catastrophic | major | moderate | minor | insignificant
Probability | 5 | almost certain | 25 | 20 | 15 | 10 | 5 | Probability | 5 | almost certain | extremeley high | extremeley high | very high | high | moderate
| 4 | likely | 20 | 16 | 12 | 8 | 4 |  | 4 | likely | extremeley high | very high | high | moderate | rather small
| 3 | possible | 15 | 12 | 9 | 6 | 3 |  | 3 | possible | very high | high | moderate | rather small
| 2 | unlikely | 10 | 8 | 6 | 4 | 2 |  | 2 | unlikely | high | moderate | rather small |  | very small
| 1 | rare | 5 | 4 | 3 | 2 | 1 |  | 1 | rare | moderate | rather small | very small | very small | negligible